## Defect Report 1
Train # | 273 | TS # |  | EM 01 20 273 |  | TC1 | M4 | M1 | M2 | M3 | TC2 | Process Stage |  | PC10 | Inspector | PRASA and Gibela |  |  |  | Date | 20/3/2025 |  | Page |  | 1 of 1
Item | Demerit Class | Defect Description | [12 empty] | Localisation Interior, underframe, roof etc |  | End [1] or [2] | Side Left [L] or Right [R] | Action Required (Ready to fix/Part needed/ NCR/ Work instruction required for special process rework ) |  |  |  | Dep Pme,Ops, Warehouse,Design,SQA | GIBELA Sign-off |  | PRASA Sign-off | Quantity | Recurring | Misdetection | Status Open / Closed
Quality Declarations
1 | C | Lower &upper body polishing incomplete | [12 empty] | EXT |  | 1 | L&R | RTF |  |  |  | GSDI
Functional Declaration
Engineering defects
1 | C | 1/4 window screws discoloration | [12 empty] | EXT |  | 1+2 | L+R | As Per DPM Discussion |  |  |  | ENG
2 | C | GENERAL : Upper panel above windows are loose | [12 empty] | INT |  | 1+2 | L+R | As Per DPM Discussion |  |  |  | ENG
3 | C | Bogie stoppers not painted inside | [12 empty] | UF |  | 1+2 | L+R | As Per DPM Discussion |  |  |  | ENG
4 | C | TC1 Above window 2 ceiling light cover not aligned | [12 empty] | INT |  | 1 | L | As Per DPM Discussion |  |  |  | ENG
5 | C | TC1 and TC2 LV1 and LV 2 Cubicles are not fixed | [12 empty] | INT |  | 1 | L+R | As Per DPM Discussion |  |  |  | ENG
6 | C | TC1 Cab ceiling not aligned with windscreen serigraph | [12 empty] | INT |  | 1 | L+2 | Under Investigation |  |  |  | ENG
Quality Defects
1 | C | TC1 LHS side skirt is sctratched | [12 empty] | EXT |  | 1 | L | RTF |  |  |  | OPS
2 | C | M2 panel above window 1 is chipped | [12 empty] | INT |  | 1 | L | RTF |  |  |  | BFG
Date |  |  |  |  | 2023-09-11
|  |  | GIB0000000380 | [5 empty] | Rev A1 |  |  |  | Defects Report | [8 empty] | 30/05/2022
4/5 Pages

## Defect Report (2) (hidden)
Train # |  | 152 | TS # |  | EM 01 20 152 | TC1 | M1 | M2 | M3 | M4 | TC2 | Process Stage |  | PC10 | Inspector | PRASA and Gibela |  |  |  | Date | 14/04/2023 |  | Page |  | 1 of 1
Item | Defect Code | Demerit Class | OPS | [11 empty] | Localisation Interior, underframe, roof etc |  | End [1] or [2] | Side Left [L] or Right [R] | Action Required (Ready to fix/Part needed/ NCR/ Work instruction required for special process rework ) |  |  |  | Dep Pme,Ops, Warehouse,Design,SQA | GIBELA Sign-off |  | PRASA Sign-off | Quantity | Recurring | Misdetection | Status Open / Closed
Date
|  |  |  | GIB0000000380 |  |  |  |  | Rev A1 |  |  |  | Defects Report | [8 empty] | 30/05/2022
4/5 Pages
This document and the information contemplated therein have to be considered as Confidential Information pursuant to the provisions of Clause 25 of the MSA, and treated as such

## Defect Report 2 (hidden)
| Train # |  | 155 | TS # |  | EM 01 20 156 | TC1 | M1 | M2 | M3 | M4 | TC2 | Process Stage |  | PC10 | Inspector | PRASA and Gibela |  |  |  | Date | 15/05/2023 |  | Page |  | 1 of 1
| Item | Defect Code | Demerit Class | OPS | [11 empty] | Localisation Interior, underframe, roof etc |  | End [1] or [2] | Side Left [L] or Right [R] | Action Required (Ready to fix/Part needed/ NCR/ Work instruction required for special process rework ) |  |  |  | Dep Pme,Ops, Warehouse,Design,SQA | GIBELA Sign-off |  | PRASA Sign-off | Quantity | Recurring | Misdetection | Status Open / Closed
Quality Defects
| 18 |  | C | [27 empty] | OPEN
| 19 |  | C | [27 empty] | OPEN
| 20 |  | C | [27 empty] | OPEN
| 21 |  | C | [27 empty] | OPEN
1 | 22 |  | C | [27 empty] | OPEN
| 23 |  | C | [27 empty] | OPEN
| 24 |  | C | [27 empty] | OPEN
| 25 |  | C | [27 empty] | OPEN
| 26 |  | C | [27 empty] | OPEN
| 27 |  | C | [27 empty] | OPEN
| 28 |  | C | [27 empty] | OPEN
| 29 |  | C | [27 empty] | OPEN
| 30 |  | C | [27 empty] | OPEN
| 31 |  | C | [27 empty] | OPEN
Date
[5 empty] | GIB0000000380 |  |  |  |  | Rev A1 |  |  |  | Defects Report | [8 empty] | 30/05/2022
4/5 Pages

## Defect Report (2) (hidden)
Train # |  | 136 | TS # |  | EM 01 20 136 | TC1 | M1 | M2 | M3 | M4 | TC2 | Process Stage |  | PC10 | Inspector | PRASA and Gibela |  |  |  | Date | 23/01/2023 |  | Page |  | 1 of 1
Item | Defect Code | Demerit Class | OPS | [11 empty] | Localisation Interior, underframe, roof etc |  | End [1] or [2] | Side Left [L] or Right [R] | Action Required (Ready to fix/Part needed/ NCR/ Work instruction required for special process rework ) |  |  |  | Dep Pme,Ops, Warehouse,Design,SQA | GIBELA Sign-off |  | PRASA Sign-off | Quantity | Recurring | Misdetection | Status Open / Closed
Quality defects
20 |  | C | TC2 Door 6 RHS leaf quarter window frame has a scratch | [11 empty] | Interior |  | 2 | RHS | NCR |  |  |  | KBSA |  |  |  | 1 |  | X
21 |  | C | TC2 driver's desk next to the line inductor button chip mark to repair | [11 empty] | Interior |  | 1 | RHS | RTF |  |  |  | OPS |  |  |  | 1 | X | X
22 |  | B | TC2 brake control panel has an air leak | [11 empty] | UF |  | 1 | RHS | NCR |  |  |  | Wabtec |  |  |  | 1 |  | X
23 |  | C | M4 marley floor has a brownish stain next to the tripod | [11 empty] | Interior |  | 1 | LHS | Investigate |  |  |  | OPS |  |  |  | 1
24 |  | C | M3 end 1 step-plate not flushing | [11 empty] | Interior |  | 1 | LHS | Investigate |  |  |  | PME/OPS |  |  |  | 1 | X
25 |  | C | TC2 mirror foams grey in color instead of black | [11 empty] | Interior |  | 1 | LHS | RTF |  |  |  | OPS |  |  |  | 1 | X | X
Quality Technician Name & Signature | [14 empty] | Production Supervisor Name & Signature
Date
|  |  |  | GIB0000000380 |  |  |  |  | Rev A1 |  |  |  | Defects Report | [8 empty] | 30/05/2022
4/5 Pages
This document and the information contemplated therein have to be considered as Confidential Information pursuant to the provisions of Clause 25 of the MSA, and treated as such

## Defects Codes (hidden)
Defects Code
Family |  | Code | Defect |  | Family |  | Code | Defect
1 | SURFACE FINISH, PAINTING and GEL COAT | 1.01 | Gloss - brightness |  | 4 | PACKING, DOCUMENTATION | 4.01 | Missing certificates - documentation
|  | 1.02 | Thickness |  |  |  | 4.02 | Packing list nonconforming
|  | 1.03 | Adherence |  |  |  | 4.03 | Missing data on documentation
|  | 1.04 | Colour variation |  |  |  | 4.04 | Missing parts
|  | 1.05 | Dirt - stain / corrosion / foreign objects |  |  |  | 4.05 | Lack of protection
|  | 1.06 | Orange peel - roughness |  |  |  | 4.06 | Damaged due to transportation
|  | 1.07 | Cracks / scratches |  |  |  | 4.07 | Defective parts
|  | 1.08 | Surface blurred - sharp edges |  |  |  | 4.08 | Packaging does not comply
|  | 1.09 | Blade cut |  | 5 | RAW MATERIAL | 5.01 | Chemical / mechanical properties
2 | WELDING | 2.01 | Porosity |  |  |  | 5.02 | Inclusions
|  | 2.02 | Spatter |  |  |  | 5.03 | Shrinkage
|  | 2.03 | Crack - arch opening |  |  |  | 5.04 | Crack
|  | 2.04 | Thickness irregularity |  |  |  | 5.05 | Porosity
|  | 2.05 | Lack of penetration |  |  |  | 5.06 | Press marks
|  | 2.06 | Undercutting |  |  |  | 5.07 | Deburring
|  | 2.07 | Blow-hole - pin hole |  |  |  | 5.08 | Missing or non compliant machining
|  | 2.08 | Underflushing |  | 6 | GLAZING | 6.01 | Joints - rubber
|  | 2.09 | Poor restart |  |  |  | 6.02 | Marking
|  | 2.10 | Non-conforming welding process |  |  |  | 6.03 | Scratches on glass
|  | 2.11 | Non-conforming loop back |  |  |  | 6.04 | Silk - screen printing NC
|  | 2.12 | Incomplete - over fusion |  |  |  | 6.05 | Laminating
3 | MECHANICAL, DIMENSIONAL, ASSEMBLY | 3.01 | Regulating problem |  |  |  | 6.06 | Stretch wrapping
|  | 3.02 | Mechanical set-up - adjustment |  |  |  | 6.07 | Visual distortion
|  | 3.03 | Noise / vibration |  | 7 | ADHESIVES APPLICATION | 7.01 | Scratches or cuts
|  | 3.04 | Blocking |  |  |  | 7.02 | Covered screw or seal
|  | 3.05 | Dimensional deviation |  |  |  | 7.03 | Alignment
|  | 3.06 | Flatness |  |  |  | 7.04 | Overlapping
|  | 3.07 | Perpendicularity |  |  |  | 7.05 | Folds
|  | 3.08 | Mass |  |  |  | 7.06 | Inclusion
|  | 3.09 | Twist |  |  |  | 7.07 | Bubbles
|  | 3.10 | Geometry |  | 8 | GLUING, SEALING / WATER RESISTANT | 8.01 | Gluing not done - marks
|  | 3.11 | Roughness |  |  |  | 8.02 | Lamination
|  | 3.12 | Parallelism |  |  |  | 8.03 | Sticking
|  | 3.13 | GAP excessive - small |  |  |  | 8.04 | Mounting defect
|  | 3.14 | Alignment - flush |  |  |  | 8.05 | Defect in the application of sealant
|  | 3.15 | Fixing |  |  |  | 8.06 | Joint defect
|  | 3.16 | Torque |  |  |  | 8.07 | Putty joint defect
|  | 3.17 | Damaged before or during assembly |  |  |  | 8.08 | Water leakage
|  | 3.18 | Clipping - fastenings |  | 9 | CABLES/WIRING | 9.01 | Cable defect
|  | 3.19 | Cleanliness |  |  |  | 9.02 | Connector-pins- lugs
|  | 3.20 | Clearance |  |  |  | 9.03 | Crimping
|  | 3.21 | Missing or wrong components |  |  |  | 9.04 | Damaged or missing isolant wrapping
|  | 3.22 | Wrong locating pin |  |  |  | 9.05 | Fixing - mounting
|  | 3.23 | Component positioning |  |  |  | 9.06 | Identification - labeling
|  | 3.24 | Identification - labelling |  |  |  | 9.07 | Distortion on Screen
[7 empty] | 9.08 | Inversion
[7 empty] | 9.09 | Non compliant isolant wrapping or cable
[7 empty] | 9.10 | Routing
DEMERIT CLASSIFICATION EXPLANATION
[6 empty] | Defects Report |  |  | 26/10/2015
|  |  | GIB0000000380 | Rev A0 |  |  |  |  | 5/5 Pages
This document and the information contemplated therein have to be considered as Confidential Information pursuant to the provisions of Clause 25 of the MSA, and treated as such
TO BE UPDATED WITH NEW GSI ALSTOM CODES