## TS216 PRASA Data Book
Mileage at PAC (KM) |  |  |  | 27 KM
PRASA - Train 01 20 216 |  |  |  | TC1 | M4 | M1 | M2 | M3 | TC2
Summary Train Level
1.0 |  | Train Configuration - Car ID |  | 01 20 216 1 | 01 20 216 2 | 01 20 216 3 | 01 20 216 4 | 01 20 216 5 | 01 20 216 6
2.0 |  | Open Points | LIMA Cristiano <cristiano.marques.lima@transport.alstom.com> | [6 empty] | 0 | 0 | 0 | 0
| 2.1 | Derogations |  | OK
| 2.2 | Consolidated Single Open Issue List |  | OK
3.0 |  | Design Changes Applied | REBELO Alberto <alberto.rebelo@transport.alstom.com> | OK | [5 empty] | 0 | 0 | 0 | 0
4.0 |  | Configuration Article Hardware List |  | OK
5.0 |  | Configuration Article Software List |  | OK
6.0 |  | Testing - Train level
| 6.1 | Train Testing |  | OK
| 6.2 | Train Acceptance Test |  | N/A
| 6.3 | Train Watertightness |  | OK
| 6.4 | Train Weight |  | OK
7 |  | Quality Acceptance - Train Defects Report Final |  | OK
Summary Car Level |  |  |  | 01 20 216 1 | 01 20 216 2 | 01 20 216 3 | 01 20 216 4 | 01 20 216 5 | 01 20 216 6
8.0 |  | Testing Report - Car level | GAVIOLLI Rafael <rafael.gaviolli@transport.alstom.com> | [6 empty] | 0 | 0 | 0 | 0
| 8.1 | Car Watertightness | Check List 022 / Check List 056 | OK | OK | OK | OK | OK | OK |  |  |  |  | 0 | #REF! | 0 | #REF!
| 8.2 | Car Levelling | Check List 052 | OK | OK | OK | OK | OK | OK
9.0 |  | PU's Documentation
| 9.1 | Carbody shell dimensions | S:\Publico\Deptos\CQ\Projetos\PRASA\History BoOK\Arquivos\10.5 LV | OK | OK | OK | OK | OK | OK | 1 | 1 | 1 | 1
| 9.2 | Bogies | S:\Publico\Deptos\CQ\Projetos\PRASA\History BoOK\Arquivos\10.2 Bogie | OK | OK | OK | OK | OK | OK | 1 | 1 | 1 | 1
| 9.3 | Propulsion Box | S:\Publico\Deptos\CQ\Projetos\PRASA\History BoOK\Arquivos\10.3 Traction Converter | N/A | OK | OK | OK | OK | N/A | 1 | 1 | 1 | 1
| 9.4 | CVS | S:\Publico\Deptos\CQ\Projetos\PRASA\History BoOK\Arquivos\10.5 LV | OK | N/A | N/A | N/A | N/A | OK | 0 | OK | NOK | N/A
| 9.5 | Cabin Structure | S:\Publico\Deptos\CQ\Projetos\PRASA\History BoOK\Arquivos\10.1 Cabin structure | OK | N/A | N/A | N/A | N/A | OK | 1 | 1 | 1 | 1