## 05 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
5 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 5
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Underframe
Investigation Section:
6 | Detailed description | Missing name plate on the propulsion box
7 | Root Causes | Received without from Supplier
8 | Comment / Action Required | Fit name plate on Propulsion box
Proposed Solution
9 | Proposed Solution: | Fit name plate on Propulsion box
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 06 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
6 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 6
3 | Car Type | All
4 | Source | PC10 Quality Snag
5 | Localisation | Underframe
Investigation Section:
6 | Detailed description | Rusting leveling rod
7 | Root Causes | Bad quality of parts fitted by Supplier
8 | Comment / Action Required | Remove and replace leveling rod with good parts
Proposed Solution
9 | Proposed Solution: | Remove and replace leveling rod with good parts
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 07 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
7 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 7
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description | RVM restricted view
7 | Root Causes | Fitting adjustments incorrect
8 | Comment / Action Required | Re-adjust RVM's
Proposed Solution
9 | Proposed Solution: | Re-adjust RVM's
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 08 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
8 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 8
3 | Car Type | All
4 | Source | PC10 Quality Snag
5 | Localisation | Int+Ext
Investigation Section:
6 | Detailed description | GSDI livery in-complete
7 | Root Causes | Unavailability of train to Supplier
8 | Comment / Action Required | Complete fitment of livery
Proposed Solution
9 | Proposed Solution: | Complete fitment of livery
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 09 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
9 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 9
3 | Car Type | All
4 | Source | PC10 Quality Snag
5 | Localisation | Underframe
Investigation Section:
6 | Detailed description | Underframe paint touch-ups
7 | Root Causes | ???
8 | Comment / Action Required | Repaint the area
Proposed Solution
9 | Proposed Solution: | Repaint the area
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 10 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
10 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 10
3 | Car Type | All
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description | Gangway self inspection incomplete
7 | Root Causes | ???
8 | Comment / Action Required | ???
Proposed Solution
9 | Proposed Solution: | ???
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 11 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
11 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 11
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description
7 | Root Causes
8 | Comment / Action Required
Proposed Solution
9 | Proposed Solution:
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 13 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
7 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 7
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description
7 | Root Causes
8 | Comment / Action Required
Proposed Solution
9 | Proposed Solution: | Re-adjust RVM's
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 14 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
7 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 7
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description
7 | Root Causes
8 | Comment / Action Required
Proposed Solution
9 | Proposed Solution: | Re-adjust RVM's
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 15 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
7 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 7
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description
7 | Root Causes
8 | Comment / Action Required
Proposed Solution
9 | Proposed Solution: | Re-adjust RVM's
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## OIL
Open Issue Single List - TS211 EM01 20 211 PAC#211
GIB000000XXXX_A0
N° | Car Type | Source | Issue Description | Responsible Party | Localisation | Status: Open/Closed | Commitment date | Actual Completion date | Rectification WorkSheet Number | PRASA Signature
avf
1 | Gen | PC11 | passenger windows with avf defects. Tc2 window 4 ,8 &10 has inclusions . Tc2 window 6 prasa logo avf has inclusions M3 window 2 &12 bottom edge is lifting M1 window 8 & 10 bottom edges are lifting M4 window 4 & 10 edges are lfiting M4 window 6 prasa logo avf has bubbles. Tc1 window 1 & 9 avf has bubbles. M4 window 5 has bubbles M4 window 7 has lifting edges M1 window 3,5& 11 has bubbles M2 window 3& 11 has bubbles M2 window 5 prasa wheel has bubbles and inclusions. M3 window 5 both interior and prasa avf have bubbles M3 window 3 has lifting edges Tc2 window 3 prasa logo has bubbles. | Gsdi | Int | Open
2 | Gen | PC11 | Passenger door avfs with defects Tc2 door 6 Rhl has bubbles. M3 door 2 Rhs has bubbles. M2 door 2 Rhl has M4 door 1,3 & 5 lhl has bubbles Tc1 door 6 lhl has inclusions Tc1 door 3 rhl has lifting edges Tc1 door 1 rhl has inclusions Tc1 door 5 lhl has inclusions M4 door 5 rhl has bubbles M4 door 3 both leafs have inclusions M2 door 5 Rhl have bubbles M2 door 1 Rhl has inclusions M3 door 1 &3 Rhl has bubbles Tc1 door 1 Lhl has bubbles and inclusions | Gsdi | EXT/Int | Open
3 | Tc1 | PC11 | Rhs platform light is delaminating | Gibela | Exterior | Open |  |  |  | Ncr
4 | Tc2 | Pc11 | Lhs cab door hinge has paint chips | Gibela | Interior | Open
5 | Gen | Pc11 | Door marley peeling off . Tc2 door 3 rhs Tc2 door 5 rhs M1 door 5 rhs M1 door 4 rhs M1 door 5 rhs M1 door 3 both side |  |  | Open
6 | Tc2 | Pc11 | Hc cubicle budget lock has a gap around it . | Gibela | Interior | Open
7 | M2 | PC11 | end 1 top end display avf has inclusions | Gibela | Interior | Open
8 | M1 | Pc11 | end 2 hc cubicle has a hole next to the door | Gibela | Interior | Open
9 | Tc1 | Pc11 | paint chip on luggage rack by windows 2,5& 10 | Gibela | Interior | Open
10 | Tc2 | Pc11 | rust on lower body next door 6 Lhl | Gibela | Exterior | Open
11 | M1 | Pc11 | scratch on lower side next to door 3 lhl | Gibela | Exterior | Open
12 | M4 | Pc11 | window3 rubber pintched | Gibela | Exterior | Open
13 | Tc1 | Pc11 | paint chip on RHS cab door bottome edge | Gibela | Exterior | Open | _
14 | Tc1 | Pc11 | window 4 rubber is buldging | Gibela | Exterior | Open
15 | Tc1 | Pc11 | door rhl rubber poorly trimmed . | Gibela | Exterior | Open
16 | M4 | PC11 | door 4 threshold has torque mark stains | Gibela | Exterior | Open
17 | M1 | Pc11 | door 5 lhl rubber is cut | Gibela | Exterior | Open
18 | M3 | Pc11 | lower body next to door 5 lhs has scratches | Gibela | Exterior | Open
19 | Tc2 | Pc11 | rust on lower body next to door 5 lhs | Gibela | Exterior | Open
20 | Tc2 | pc11 | ddu screen screw not flushed | Gibela | Interior | Open
21 | Tc2 | Pc11 | cab end pis glass is detaching | Gibela | Interior | Open
22 | M3 | Pc11 | end 1 top end pisplay is deleminating | Gibela | Interior | Open
23 | M2 | Pc11 | roof arch above window 1 has paint chips | Gibela | Interior | Open
24 | M4 | Pc11 | lv4 loose next end finisher bracket | Gibela | Interior | Open
25 | Tc1 | Pc11 | cab door hinge protector is not secured | Gibela | Interior | Open
26 | GEN | Pc11 | loose roof arches above window m1 window 1 3 & 11 . M4 window 1 Tc1 window 2 & 23 . | Gibela | Interior | Open
Engineering isuues
1 | Gen | PC11 | outter gangway belows uneven folds | Gibela | Exterior | open |  |  |  | As per DPM #84 discussions
2 | Gen | PC11 | Passenger door window screws discolouring | Gibela | Exterior | open |  |  |  | As per DPM #84 discussions
5 | Gen | PC11 | Loose upper panels | Gibela | Interior | open |  |  |  | As per DPM #84 discussions
FLEET DEFECTS
5 | Gen | Fleet Defects | None | [6 empty] | As per the revised fleet defect rectification plans
SIGNED OF BEHALF OF PRASA |  |  |  |  | SIGNED OF BEHALF OF GIBELA
Signature: …………………………………………………….. Name: Vuyisile SIDYIYO The Project Managers Representative Date: Place: |  |  |  |  | Signature: …………………………………………………….. Name: Devendran GOVENDER The Engineers Representative Date: Place: