## 05 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
5 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 5
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Underframe
Investigation Section:
6 | Detailed description | Missing name plate on the propulsion box
7 | Root Causes | Received without from Supplier
8 | Comment / Action Required | Fit name plate on Propulsion box
Proposed Solution
9 | Proposed Solution: | Fit name plate on Propulsion box
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 06 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
6 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 6
3 | Car Type | All
4 | Source | PC10 Quality Snag
5 | Localisation | Underframe
Investigation Section:
6 | Detailed description | Rusting leveling rod
7 | Root Causes | Bad quality of parts fitted by Supplier
8 | Comment / Action Required | Remove and replace leveling rod with good parts
Proposed Solution
9 | Proposed Solution: | Remove and replace leveling rod with good parts
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 07 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
7 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 7
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description | RVM restricted view
7 | Root Causes | Fitting adjustments incorrect
8 | Comment / Action Required | Re-adjust RVM's
Proposed Solution
9 | Proposed Solution: | Re-adjust RVM's
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 08 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
8 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 8
3 | Car Type | All
4 | Source | PC10 Quality Snag
5 | Localisation | Int+Ext
Investigation Section:
6 | Detailed description | GSDI livery in-complete
7 | Root Causes | Unavailability of train to Supplier
8 | Comment / Action Required | Complete fitment of livery
Proposed Solution
9 | Proposed Solution: | Complete fitment of livery
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 09 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
9 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 9
3 | Car Type | All
4 | Source | PC10 Quality Snag
5 | Localisation | Underframe
Investigation Section:
6 | Detailed description | Underframe paint touch-ups
7 | Root Causes | ???
8 | Comment / Action Required | Repaint the area
Proposed Solution
9 | Proposed Solution: | Repaint the area
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 10 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
10 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 10
3 | Car Type | All
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description | Gangway self inspection incomplete
7 | Root Causes | ???
8 | Comment / Action Required | ???
Proposed Solution
9 | Proposed Solution: | ???
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 11 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
11 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 11
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description
7 | Root Causes
8 | Comment / Action Required
Proposed Solution
9 | Proposed Solution:
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 13 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
7 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 7
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description
7 | Root Causes
8 | Comment / Action Required
Proposed Solution
9 | Proposed Solution: | Re-adjust RVM's
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 14 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
7 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 7
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description
7 | Root Causes
8 | Comment / Action Required
Proposed Solution
9 | Proposed Solution: | Re-adjust RVM's
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 15 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
7 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 7
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description
7 | Root Causes
8 | Comment / Action Required
Proposed Solution
9 | Proposed Solution: | Re-adjust RVM's
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## OIL
Open Issue Single List - TS213 EM01 20 213 PAC#213
GIB000000XXXX_A0
N° | Car Type | Source | Issue Description | Responsible Party | Localisation | Status: Open/Closed | Commitment date | Actual Completion date | Rectification WorkSheet Number | PRASA Signature
avf
1 | Gen | PC11 | Passenger door avfs with defects: Tc2 door 1 rhl avf has lifting edges M3 door 1 rhl avf has lifting edges m3 door 5 rhl avf has lifting edges M4 door 6 rhl avf has lifting iedges Tc2 door 2 LHL has bubbles M3 door 4 RHl has inclusions M1 door 3 lhl has inclusions Tc1 door 1 both leafs has lifting edges and inclusions M3 door 2 Lhl has lifting edges M1 door 5 both leafs has lifting edges. M4 door 1 both leafs have inclusions and lifting edges | Gsdi | Interior | Open
2 | Gen | PC11 | Passenger windows avfs with defects Tc2 window 7 avf has bubbles and lifting edges M4 window 6 avf is lifting M4 window 8 prasa wheel window section has bubbles Tc2 window 10 has bubbles M2 window 12 has inclusions M4 window 3 has inclusions Tc1 window 3 has iclusion on both interior and prasa wheel avf. Tc2 window 8 has lifting edges M1 window 11 has lifting edges M1 window 3 has lifting edges M1 window 1 has inclusions Tc1 window 1 has lifting edges M4 window 9 has lifting edges | Gsdi | Exterior | Open
3 | M2/M1 | PC11 | door 6 LHL sealent residue & M1 door 4 rhl | Gibela | Exterior | Open
4 | M1 | PC11 | Door 2 sealent residue and rust mark on the rhs | Gibela | Exterior | Open
5 | Tc1 | PC11 | Window 10 luggage rack has paint scratches | Gibela | Interior | Open
6 | M1 | PC11 | Hc cubicle 400v sticker is skew | Gsdi | Interior | Open
7 | M2 | PC11 | window 2 luggage rack bracket has a paint chip at the top | Gibela | Interior | Open
8 | Tc2 | PC11 | Door 4 lhs door marley has detached | Gibela | Interior | Open
9 | Tc1/ Tc2 | PC11 | footrest not resetting | Gibela | Interior | Open
10 | Tc2 | PC11 | sunshade moves out of the brackets | Gibela | Interior | Open
11 | Tc2 | PC11 | Black paint has inclusions above alstom badge below rear mirror | Gibela | Exterior | Open
12 | M3 | PC11 | RHS budget lock not locking on Lvbox LHS | Gibela | Underframe | Open | _
13 | M1 | PC11 | panto control cover has a damaged budget lock lhs | Ubunye | Underframe | Open
14 | Tc1 | PC11 | Door 6 incomplete repair on roof arch next to budget lock | BFG | Interior | Open
15 | M4 | PC11 | Object stcu inside light cover above window 3 & 5 and a misaligned gap. | Gibela | Interior | Open
16 | Gen | PC11 | Loose budget locks on roof archs M4 door 6 M2 door 1,2,3,4 &6 M3 door 3,4,&5 Tc1 door 4 &5 | Gibela | Interior | Open
17 | M1 | PC11 | Lv3,1 loose budget lock | Gibela | Interior | Open
18 | M1 | PC11 | Rattling hanbar bewtwen windows 8& 10 | Gibela | Interior | Open
19 | M2 | PC11 | end 1 pis display has inclusions on the avf and rough edegs on ceiling panel | Gsdi/Gibela | Interior | Open
20 | Tc1 | PC11 | yellow stain below seat below window 9. | Gibela | Interior | Open
21 | Tc2 | PC11 | cab door avf top window avf has inclusions Rhs and Tc1 left side | Gibela | Interior | Open
22 | M1 | PC11 | end 1 blue vynal has folds lhs | Gsdi | Exterior | Open
23 | Tc1 | PC11 | scratch on cab door handle area | Gibela | Exterior | Open
24 | Tc1 | PC11 | rust on wiper connectors | Gibela | Exterior | Open
25 | M3 | PC11 | door 5 lhs door marley detaching | Gibela | Interior | Open
26 | Tc2 | PC11 | loose roof arch above window 7 | Gibela | Interior | Open
27 | Tc2 | PC11 | lower body below window 10 is scratched | Gsdi | Exterior | Open
28 | M4 | PC11 | lower body below window 1 is poorly polished | Gsdi | Exterior | Open
29 | Tc1 | PC11 | lhs cab door avf has inclusions | Gsdi | Interior | Open
30 | Tc1 | PC11 | Lv1,1 front door rattling and passage door top budget lock not closing | Gibela | Interior | Open
31 | Gen | PC11 | seats with defects Tc1 below window 1 & 2 grey seats scratched M4 below window 3 seat to be polished M1 below window 9 seat to be polished | Gibela | Interior | Open
32 | Tc1 | PC11 | Hc cubicle has poor rework on the bottom edge . | BFG | Interior | Open
33 | Tc1 | PC11 | end 2 top end lining is sagging | Gibela | Interior | Open
34 | Gen | PC11 | Rattling draft screens M4 next to Lv3,1 M1 next to hc cubicle M3 next to door 5 window 9 Tc2 next to Hc cubicle Tc2 next to window 7 door 5 Tc2 next window 5 door 3 Tc2 next to window 2 ddor 2 | Gibela | Interior | Open
Engineering isuues
1 | Gen | PC11 | outter gangway belows uneven folds | Gibela | Exterior | open |  |  |  | As per DPM #84 discussions
2 | Gen | PC11 | Passenger door window screws discolouring | Gibela | Exterior | open |  |  |  | As per DPM #84 discussions
5 | Gen | PC11 | Loose upper panels | Gibela | Interior | open |  |  |  | As per DPM #84 discussions
FLEET DEFECTS
5 | Gen | Fleet Defects | None | [6 empty] | As per the revised fleet defect rectification plans
SIGNED OF BEHALF OF PRASA |  |  |  |  | SIGNED OF BEHALF OF GIBELA
Signature: …………………………………………………….. Name: Vuyisile SIDYIYO The Project Managers Representative Date: Place: |  |  |  |  | Signature: …………………………………………………….. Name: Devendran GOVENDER The Engineers Representative Date: Place: