## 05 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
5 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 5
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Underframe
Investigation Section:
6 | Detailed description | Missing name plate on the propulsion box
7 | Root Causes | Received without from Supplier
8 | Comment / Action Required | Fit name plate on Propulsion box
Proposed Solution
9 | Proposed Solution: | Fit name plate on Propulsion box
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 06 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
6 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 6
3 | Car Type | All
4 | Source | PC10 Quality Snag
5 | Localisation | Underframe
Investigation Section:
6 | Detailed description | Rusting leveling rod
7 | Root Causes | Bad quality of parts fitted by Supplier
8 | Comment / Action Required | Remove and replace leveling rod with good parts
Proposed Solution
9 | Proposed Solution: | Remove and replace leveling rod with good parts
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 07 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
7 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 7
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description | RVM restricted view
7 | Root Causes | Fitting adjustments incorrect
8 | Comment / Action Required | Re-adjust RVM's
Proposed Solution
9 | Proposed Solution: | Re-adjust RVM's
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 08 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
8 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 8
3 | Car Type | All
4 | Source | PC10 Quality Snag
5 | Localisation | Int+Ext
Investigation Section:
6 | Detailed description | GSDI livery in-complete
7 | Root Causes | Unavailability of train to Supplier
8 | Comment / Action Required | Complete fitment of livery
Proposed Solution
9 | Proposed Solution: | Complete fitment of livery
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 09 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
9 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 9
3 | Car Type | All
4 | Source | PC10 Quality Snag
5 | Localisation | Underframe
Investigation Section:
6 | Detailed description | Underframe paint touch-ups
7 | Root Causes | ???
8 | Comment / Action Required | Repaint the area
Proposed Solution
9 | Proposed Solution: | Repaint the area
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 10 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
10 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 10
3 | Car Type | All
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description | Gangway self inspection incomplete
7 | Root Causes | ???
8 | Comment / Action Required | ???
Proposed Solution
9 | Proposed Solution: | ???
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 11 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
11 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 11
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description
7 | Root Causes
8 | Comment / Action Required
Proposed Solution
9 | Proposed Solution:
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 13 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
7 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 7
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description
7 | Root Causes
8 | Comment / Action Required
Proposed Solution
9 | Proposed Solution: | Re-adjust RVM's
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 14 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
7 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 7
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description
7 | Root Causes
8 | Comment / Action Required
Proposed Solution
9 | Proposed Solution: | Re-adjust RVM's
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## 15 (hidden)
Sht # | RECTIFICATION WORK - Open Issue Single List - TS22 EM01 10 022 PAC#20
7 | PRASA information:
1 | Reference Document No. / Version | GIB0000001445
2 | Minor Defect Item No. | 7
3 | Car Type | TC1 & TC2
4 | Source | PC10 Quality Snag
5 | Localisation | Exterior
Investigation Section:
6 | Detailed description
7 | Root Causes
8 | Comment / Action Required
Proposed Solution
9 | Proposed Solution: | Re-adjust RVM's
10 | Interim solution required/possible? - Containment action | [No]
11 | Impact on Maintenance? | [No]
12 | Commitment Date | 2019-03-22
13 | Solution accepted by PRASA (date)
Rectification Work Complete:
14 | Minor Defect eliminated | [Yes]
15 | Witnessed by PRASA (date)
RECTIFICATION WORK IN RESPECT OF THE ABOVE REFERENCED NEW TRAIN HAS BEEN COMPLETED
| SIGNED ON BEHALF OF PRASA | SIGNED ON BEHALF OF GIBELA
| …………………………………………………………………………. | ………………………………………………………………………….
| Signature | Signature
| …………………………………………………………………………. | ………………………………………………………………………….
| Name | Name
| …………………………………………………………………………. | ………………………………………………………………………….
| Designation | Designation
| …………………………………………………………………………. | ………………………………………………………………………….
| Date | Date

## OIL
Open Issue Single List - TS214 EM01 20 214 PAC#214
GIB000000XXXX_A0
N° | Car Type | Source | Issue Description | Responsible Party | Localisation | Status: Open/Closed | Commitment date | Actual Completion date | Rectification WorkSheet Number | PRASA Signature
avf
1 | Tc1 | PC11 | Horn cover has a scratch on bottom edge | Gibela | Exterior | Open
2 | Gen | PC11 | window avf defects. M1 window 9 and 11 have lifting edges M3 window 4 has bubbles and edges M2 window 4 avf has lifitng edges Tc2 window 9 avf has bubbles. Tc2 window 6 has bubbles and lifting edges Tc2 window 3 avf has bubbles on prasa wheel avf M1 window 4& 10 avf has inclusions Tc1 window 2 avf has lifting edges M1 window 5 has bubbles Tc2 window 2 has lifting edges | Gsdi | Interior | Open
3 | Gen | PC11 | Quarter window avf with defects. Tc2 door 5 RHL avf has lifting edges M1 door 1 lhl has lifting edges M3 Door 1 both leafs avf have lifting edges M2 door 1 both leafs have lifting edges Tc1 door 3 lhl has bubbles | Gsdi | Interior | Open
4 | Tc1 | PC11 | luggage rack ,console has paint chips above window 9 | Gibela | Interior | Open
5 | Gen | PC11 | Detaching door marley. | BFG | Interior | Open
6 | Tc1 | PC11 | Lhs rear view mirror not flushed | Gibela | Exterior | Open
7 | Tc1 | PC11 | Lhs cab door both avfs have inclusions | Gsdi | Interior | Open
8 | Tc1 | PC11 | Lhs Lvbox cover x2 budget locks not locking. | Gibela | Underframe | Open
9 | Gen | PC11 | solebar sharp edges | Gibela | Underframe | Open
10 | Gen | PC11 | Installation paint damage on the underframe equipment brackets | Gibela | Underframe | Open
11 | Tc1 /m4 | PC11 | LHS outter gangway poorly fitted. ( loose bolts ) | Gibela | Exterior | Open
12 | M4 | PC11 | scratches on lower body side by door 1 | Gsdi | Exterior | Open | _
13 | M1 | PC11 | sharp weld spatter on lower body side below window 3 | Gibela | Exterior | Open
14 | M2 | PC11 | scartch and grinding on lower bosy side below windows 4 &6 | Gsdi | Exterior | Open
15 | Tc2 | PC11 | grinding marks on lower body side below windows 6,8 &10. | Gsdi | Exterior | Open
16 | Tc2 | PC11 | Nose panel not aligned | Gibela | Exterior | Open
17 | M4 | PC11 | Edge of black vynal lifting below window 2 | Gsdi | Exterior | Open
18 | Tc1 | PC11 | RHS cab door has inclusions under top window avf | Gsdi | Interior | Open
19 | M4 | PC11 | end 1 rhs poor paint repair on LV6 by top end lining | BFG | Interior | Open
20 | Gen | PC11 | Rattling draft screens M4 by window 11 /end 2 M2 by window 8/door 4 M3 by window 4/door 2 M2 by window 2 /end 1 | Gibela | Interior | Open
21 | M1 | PC11 | Lv3,2 side cover gap is too wide | Gibela | Interior | Open
22 | M2 | PC11 | end 2 top end lining sagging by gangway | Gibela | Interior | Open
23 | M2 | PC11 | Door 3 roof arch center lock not locating | Gibela | Interior | Open
24 | M2 | PC11 | Lv4 side cover gap too wide | Gibela | Interior | Open
25 | M2 | PC11 | end 2 Pis display is delaminating | Gibela | Interior | Open
26 | M3 | PC11 | paint chip on luggage rack bracket by windows 7 &9. | Gibela | Interior | Open
27 | M3 | PC11 | Paint damage on window 3 center panel | Gibela | Interior | Open
28 | M3 | PC11 | end 1 pis display perspex is scratched | Gibela | Interior | Open
29 | Tc2 | PC11 | Rhs cab door not opening with key | Gibela | Exterior | Open
30 | Tc2 | PC11 | lhs cab door top window avf has inclusion | Gsdi | Exterior | Open
31 | Tc1 | PC11 | scratch on driver desk | Gibela | Interior | Open
32 | Tc1 | PC11 | paint chip on upper panel by window 10 | BFG | Interior | Open
33 | Gen | PC11 | missing top end lining avf M2 end 2 M2 end 1 M3 end 2 Tc2 end 2 | Gibela | Interior | Open
34 | M2 | PC11 | Lv3,3 side cover budget lock not locking | Gibela | Interior | Open
35 | M2 | PC11 | end 1 top end lining LED metal cover is missing locking screws | Gibela | Interior | Open
36 | M3 | PC11 | Dirt inside light cover above door 4 | Gibela | Interior | Open
37 | Tc2 | PC11 | PIS display avf has bubbles. | Gsdi | Interior | Open
Engineering isuues
1 | Gen | PC11 | outter gangway belows uneven folds | Gibela | Exterior | open |  |  |  | As per DPM #84 discussions
2 | Gen | PC11 | loose upper panels | Gibela | Interior | Open |  |  |  | As per DPM #84 discussions
3 | Gen | PC11 | horn covers not flushed | Gibela | Exterior | open |  |  |  | As per DPM #84 discussions
4 | Gen | PC11 | Inner gangway bolts exposed connection body end | Gibela | Interior | open |  |  |  | As per DPM #84 discussions
FLEET DEFECTS
5 | Gen | Fleet Defects | None | [6 empty] | As per the revised fleet defect rectification plans
SIGNED OF BEHALF OF PRASA |  |  |  |  | SIGNED OF BEHALF OF GIBELA
Signature: …………………………………………………….. Name: Vuyisile SIDYIYO The Project Managers Representative Date: Place: |  |  |  |  | Signature: …………………………………………………….. Name: Devendran GOVENDER The Engineers Representative Date: Place: